## UCP
Paquete | Puntos de Caso de Uso - Use Case Points
Unadjusted Use Case Points:
Análisis de Actores
Complejidad | Definición | Peso | Cantidad | Peso Total
Simple | Representa otro sistema con una interfase definida de aplicación programada | 1 | 1 | 1
Promedio | Interactúa con otra aplicación a través de un protocolo o interacción humana a través de terminal de línea | 2 | 0 | 0
Complejo | Interacción humana a través de interfase usuario gráfica | 3 | 2 | 6
TOTAL |  |  | 3 | 7
Análisis de Casos de Uso
Complejidad | Definición | Peso | Cantidad | Peso Total
Simple | Tiene 3 o menos transacciones incluyendo cursos alternativos. Casos de uso con menos de 5 objetos de análisis | 5 | 3 | 15
Promedio | Tiene 3 a 7 transacciones incluyendo cursos alternativos. Casos de uso con 5 a 10 objetos de análisis | 10 | 4 | 40
Complejo | Tiene más de 7 transacciones incluyendo cursos alternativos. Casos de uso con más de 10 objetos de análisis | 15 | 2 | 30
TOTAL |  |  | 9 | 85
Total de Unadjusted Case Points |  |  |  | 92
Adjusted Use Case Points: AUCP = UUCP × TCF × EF |  |  |  | 82.0157
Esfuerzo Estimado en horas: AUCP x 8 |  |  |  | 656.1256 | Hs. | 3.9055 | meses/hombre
| Fases: |  |  |  |  | Precio x Hora
Analista | Especificación |  | 5% | 32.8063 | Hs. | 400 | 13122.512
| Análisis |  | 10% | 65.6126 | Hs. | 400 | 26245.024
AnalistaProgr | Diseño |  | 10% | 65.6126 | Hs. | 700 | 45928.792
Programador | Construcción |  | 50% | 328.0628 | Hs. | 300 | 98418.84
Soporte | Integración |  | 5% | 32.8063 | Hs. | 200 | 6561.256
Tester | Pruebas |  | 15% | 98.4188 | Hs. | 200 | 19683.768
Lider | Administración |  | 5% | 32.8063 | Hs. | 1000 | 32806.28
|  |  | 100% | 656.1256 | Hs. |  | 242766.472

## TCF
Factor de Complejidad Técnica -Technical Complexity Factor (TCF)
Factor | Descripción | Peso | Valor Asig. | Factor Calc | Comentarios
T1 | Sistema Distribuido | 2 | 0 | 0 | Central system
T2 | Tiempo de Respuesta, objetivos de performance | 1 | 3 | 3 | Speed is probably limited by human input
T3 | Eficiencia de Usuario Final | 1 | 5 | 5 | Needs to be efficient
T4 | Complejidad de procesamiento interno | 1 | 1 | 1 | No complex calculations
T5 | Codigo debe ser reusable | 1 | 0 | 0 | No
T6 | Easy to install | 0.5 | 0 | 0 | It's a website, no installation required
T7 | Easy to use | 0.5 | 5 | 2.5 | Very user-friendly
T8 | Portable | 2 | 0 | 0 | No
T9 | Easy to change | 1 | 4 | 4 | Low maintenance cost
T10 | Concurrent | 1 | 0 | 0 | No
T11 | Includes special security objectives | 1 | 3 | 3 | Normal security
T12 | Provides direct access for third parties | 1 | 5 | 5 | WEB users have direct access
T13 | Special user training facilities are required | 1 | 1 | 1 | Few internal users, easy to use system
Total Technical factor (Tfactor): |  |  |  | 24.5
0.845
TCF = 0.6 + (.01 × TFactor)
TCF = 0.6 + (.01 × 24.5) = 0.6 + 0.245 = 0.845

## EF
Factor de Entorno -Environment Factor (EF)
Factor | Descripción | Peso | Valor Asig. | Factor Calc | Comentarios
E1 | Familiar with the project model that is used | 1.5 | 4 | 4 | Most staff is not familiar with database systems
E2 | Application experience | 0.5 | 4 | 2 | Most staff has little experience with web apps.
E3 | Object-oriented experience | 1 | 1 | 1 | All staff has sat for at least one OOP course
E4 | Lead analyst capability | 0.5 | 5 | 2.5 | Lead analyst has little experience
E5 | Motivation | 1 | 2 | 2 | The team is highly motivated
E6 | Stable requirements | 2 | 2 | 3 | Requirements seem to be mostly static
E7 | Part-time staff | -1 | 0 | 0 | No part-time staff employed
E8 | Difficult programming language | -1 | 3 | -3 | Javascript+CSS+HTML combo
Total Environment Factor (Efactor): |  |  |  | 11.5
EF = 1.4+(-0.03 × EFactor) |  |  |  | 1.055
EF = 1.4 + (-0.03 × 12) = 1.04 - 0.285 = 0.755

## Act y CU
| NOTA: Completar con los datos del Paquete | Complejidad
| Actores | Baja | Media | Alta
1 | Usuario | 1
2 | SysAdmin |  | 2
3 | Proveedor |  | 3
| Total Actores por Complejidad | 1 | 5 | 0
Complejidad
| Caso de Uso | Baja | Media | Alta
1 | ABM de Usuario | 2
2 | Login de usuario | 1
3 | Búsqueda de espectáculo |  | 3
4 | Listar espectáculos | 3
5 | Agregado al carrito de compras |  | 2
6 | Confirmación de compras |  |  | 1
7 | ABM de proveedor | 2
8 | ABM de espectáculos por proveedor |  |  | 2
9 | Login de proveedor | 1
| Total Casos de Uso por Complejidad | 9 | 5 | 3